## Guide
IAC GLOBAL PROFESSIONAL INTERNSHIP
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop

## Project Schedule
IAC Internship Progra 2023 - Machine Learning Project Schedule
|  | PROJECT START DATE | 2026-02-04
|  | Display Week Sr No | 2026-01-04 | [10 empty] | 368230 | [6 empty] | 368237 | [6 empty] | 368244 | [6 empty] | 368251 | [6 empty] | 368258 | [6 empty] | 368265 | [6 empty] | 368272 | [6 empty] | 368279 | [6 empty] | 368286
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | time axis 368230 to 368292
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 368230 to 368292
1 | Week 1 :Requirement Understanding & Planning
1 |  | Studied the given problem statement in detail to understand the objectives of predicting student graduation and placement outcomes. Identified the key challenges faced by students due to lack of career guidance. |  |  |  |  | 2026-02-04 |  |  |  | Completed
2 |  | Conducted research on similar machine learning projects related to career prediction and student performance analysis. Reviewed existing solutions and identified gaps. |  |  |  |  | 2026-05-02 |  |  |  | Completed
3 |  | Listed the important features required for the model such as CGPA, coding skills, communication skills, and extracurricular activities. Defined the structure of the dataset. |  |  |  |  | 2026-06-02 |  |  |  | Completed
4 |  | Selected the technology stack including Python, Pandas, NumPy, Scikit-learn, and Streamlit. Installed required libraries and set up the development environment. |  |  |  |  | 2026-07-02 |  |  |  | Completed
5 |  | Prepared a project plan and timeline. Documented the workflow and finalized the approach for executing the project. |  |  |  |  | 2026-08-02 |  |  |  | Completed
2 | Week 2: Data Collection
1 |  | Searched for relevant datasets from online platforms such as Kaggle and other sources related to student placement and career prediction. |  |  |  |  | 2026-11-02 |  |  |  | Completed
2 |  | Downloaded the dataset and explored its structure, including rows, columns, and data types. |  |  |  |  | 2026-02-12 |  |  |  | Completed
3 |  | Analyzed the dataset to understand each feature and its importance in predicting outcomes. |  |  |  |  | 13/02/2026 |  |  |  | Completed
4 |  | Modified the dataset by adding/removing features to align it with the project objectives. |  |  |  |  | 14/02/2026 |  |  |  | Completed
5 |  | Finalized the dataset for further processing and saved it in a suitable format for analysis. |  |  |  |  | 15/02/2026 |  |  |  | Completed
3 | Week 3 : Data Preprocessing
1 |  | Loaded the dataset into the Python environment using Pandas and verified its contents. |  |  |  |  | 17/02/2026 |  |  |  | Completed
2 |  | Handled missing values by applying appropriate techniques such as filling or removing null entries. |  |  |  |  | 18/02/2026 |  |  |  | Completed
3 |  | Removed duplicate records and corrected inconsistencies in the dataset. |  |  |  |  | 19/02/2026 |  |  |  | Completed
4 |  | Converted categorical variables into numerical format using encoding techniques. |  |  |  |  | 20/02/2026 |  |  |  | Completed
5 |  | Normalized and scaled the data to ensure uniformity across features. |  |  |  |  | 21/02/2026 |  |  |  | Completed
4 | Week4 : Data Preprocessing
1 |  | Performed initial data analysis to understand distributions and basic statistics of the dataset. |  |  |  |  | 24/02/2026 |  |  |  | Completed
2 |  | Created visualizations such as graphs and charts to analyze relationships between CGPA and placement status. |  |  |  |  | 25/02/2026 |  |  |  | Completed
3 |  | Analyzed the impact of skills and extracurricular activities on career outcomes. |  |  |  |  | 26/02/2026 |  |  |  | Completed
4 |  | Identified correlations between different features using correlation matrices. |  |  |  |  | 27/02/2026 |  |  |  | Completed
5 |  | Documented key insights obtained from the analysis for model building. |  |  |  |  | 28/02/2026 |  |  |  | Completed
5 | Week5 : Feature Engineering
1 |  | Selected the most relevant features that contribute significantly to prediction. |  |  |  |  | 2026-03-01 |  |  |  | Completed
2 |  | Removed unnecessary or redundant columns from the dataset. |  |  |  |  | 2026-03-02 |  |  |  | Completed
3 |  | Created new features where required to improve model performance. |  |  |  |  | 2026-03-03 |  |  |  | Completed
4 |  | Split the dataset into training and testing sets. |  |  |  |  | 2026-03-04 |  |  |  | Completed
5 |  | Prepared the final dataset for model training. |  |  |  |  | 2026-03-05 |  |  |  | Completed
6 | Week6 :Model Building (Basic Models)
1 |  | Implemented Logistic Regression model for classification of placement status. |  |  |  |  | 2026-03-06 |  |  |  | Completed
2 |  | Built a Decision Tree model and analyzed its performance. |  |  |  |  | 2026-03-07 |  |  |  | Completed
3 |  | Compared the performance of both models using evaluation metrics. |  |  |  |  | 2026-03-08 |  |  |  | Completed
4 |  | Tuned hyperparameters to improve model accuracy. |  |  |  |  | 2026-03-09 |  |  |  | Completed
5 |  | Selected the best-performing basic model. |  |  |  |  | 2026-03-10 |  |  |  | Completed
7 | Week7 :Advanced Model
1 |  | Implemented Random Forest algorithm to improve prediction accuracy. |  |  |  |  | 2026-03-13 |  |  |  | Completed
2 |  | Evaluated the Random Forest model and compared it with previous models. |  |  |  |  | 2026-03-14 |  |  |  | Completed
3 |  | Performed further tuning and optimization of the model. |  |  |  |  | 2026-03-15 |  |  |  | Completed
4 |  | Selected the final model based on performance comparison. |  |  |  |  | 2026-03-16 |  |  |  | Completed
5 |  | Saved the trained model using pickle for future use. |  |  |  |  | 2026-03-17 |  |  |  | Completed
8 | Week8 :Model Evaluation
1 |  | Calculated accuracy of the final model. |  |  |  |  | 2026-03-20 |  |  |  | Completed
2 |  | Generated confusion matrix to evaluate classification performance. |  |  |  |  | 2026-03-21 |  |  |  | Completed
3 |  | Calculated precision, recall, and F1-score. |  |  |  |  | 2026-03-22 |  |  |  | Completed
4 |  | Tested the model using sample inputs to verify predictions. |  |  |  |  | 2026-03-23 |  |  |  | Completed
5 |  | Documented all evaluation results. |  |  |  |  | 2026-03-24 |  |  |  | Completed
9 | Week9 :Deployment (Streamlit Application)
1 |  | Installed and configured Streamlit for application development. |  |  |  |  | 2026-03-27 |  |  |  | Completed
2 |  | Designed user interface with input fields for student data. |  |  |  |  | 2026-03-28 |  |  |  | Completed
3 |  | Integrated the trained model with the Streamlit application. |  |  |  |  | 2026-03-29 |  |  |  | Completed
4 |  | Displayed prediction results and career recommendations. |  |  |  |  | 2026-03-30 |  |  |  | Completed
5 |  | Tested the application for correctness and usability. |  |  |  |  | 2026-03-31 |  |  |  | Completed
10 | Week10 :Documentation & Finalization
1 |  | Prepared detailed project report including all sections. |  |  |  |  | 2026-04-01 |  |  |  | Completed
2 |  | Created PowerPoint presentation for project demonstration. |  |  |  |  | 2026-04-02 |  |  |  | Completed
3 |  | Prepared answers for viva questions. |  |  |  |  | 2026-04-03 |  |  |  | Completed
4 |  | Performed final testing and improvements in the system. |  |  |  |  | 2026-04-04 |  |  |  | Completed
5 |  | Completed project submission and reviewed all deliverables. |  |  |  |  | 2026-04-05 |  |  |  | Completed
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you

## EXAMPLE
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Job Cloud |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Job Cloud Job Portal
PROJECT SCOPE
PROJECT START DATE | 2026-04-02
PROJECT END DATE | 2026-09-04
OVERALL PROGRESS | In Progress
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.2 Recruit a team |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.3 Create a project charter |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.4 Requirement gathering |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
2 Planning
| 2.1 Approval of business process |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.2 Baseline project plan |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2020-12-01 | 20/1/2020 | 8 | COMPLETED
| 3.2 Build |  | 22/1/2020 | 22/3/2020 | 59 | IN PROGRESS
| 3.2.1 Features |  | 22/1/2020 | 31/1/2020 | 9
Registration of candidate and employer
Login for candidate and employer
| Home page layout |  | 2020-01-02 | 2020-10-02 | 10
Navigation bar with logo
Home
Jobs
| Candidates |  | 2020-11-02 | 15/2/2020 | 5
List of candidates with information
| Employer |  | 16/2/2020 | 21/2/2020 | 5
List of employers with information
Advance search bar
Keyoword
Upload resume
Job categories
| Job listing/ Job result page |  | 22/2/2020 | 26/2/2020 | 4
Employer name
Job category & type information
Date & location
Favorite
Apply filter & sort
| Apply for job/ Jobs tag |  | 26/2/2020 | 29/2/2020 | 3
Employer information
Deadline of application
Job details
Job description
Role
Required skills
| Footer |  | 2020-01-03 | 2020-09-03 | 8
Quick links for candidate & employer
Legal and company information
Social media follow
| Profile |  | 2020-10-03 | 15/3/2020 | 5
Dashboard
Job alerts
Applied jobs/Posted jobs
Favorite jobs/candidates
Basic information of candidate/employer
| Post job |  | 16/3/2020 | 22/3/2020 | 7
Job title and desciption
Job category and type
Required skills and application deadline
Salary and qualification
Location
| 3.3 Testing |  | 25/03/2020 | 31/3/2020 | 6
3.3.1 Manual testing
3.3.2 Automation testing
| 4 Closure |  | 2020-01-04 | 2020-01-04 | 1